## Slide 1: Funders Advisory Panel
1 August 2024
Classification: CONFIDENTIAL

## Slide 2: Housekeeping Items
Virtual Meeting Etiquette:
Please turn on your camera if possible and please turn off your mic when you are not speaking. Please kindly raise your 'virtual hand' if you would like to speak, and state your affiliation first, or you can type your questions in Chat.
Competition Law:
Many of you are from competitor organisations. As you will be aware it is critical that we all comply with competition law. If you are in any doubt about competition law compliance you should consult your compliance team.
The discussions between the attendees should be limited to discussing issues of general concern and you must not share or discuss any information that is commercially sensitive and not in the public domain – that includes: current or future prices, strategies, matters about customers or suppliers.
You can and should share your expertise about the matters that are specific to today’s agenda and can talk about matters that are public.
If any topic is raised which you feel uncomfortable discussing, please make this known and we will immediately adjourn discussions on that point.

## Slide 3: Agenda
Funders Advisory Panel Agenda Items
Minutes of meeting 8 July
Terms of Reference
Financial forecast
Review of JROC Workplan Implementation Group Agenda
Plan on a page
Programme status update
Procurement approach for MLA legal support
Broader workplan overview
AOB

## Slide 4: Minutes from 8 July

## Slide 5: Terms of reference

## Slide 6: Terms of reference
See separate Word doc for the latest draft of the Funders Advisory Panel Terms of Reference
The ToR remains in draft format pending review by JROC
The ToR is included here for reference and any further comments from FAP members

## Slide 7: Financial forecast

## Slide 8: Budget for 6 months
The total Budget costs for 6 months is c£1.65m.This is based on the current JROC workplan and assumptions, that is currently being agreed.
Governance/central office costs caters for the proposed interim governance arrangement. In November, we have an allocation for potential recruitment fees related to expanded governance from Dec'24 (if required).
JROC Workstream costs – refer to next slide for breakdown by workstream.
Support functions represent the support functions and general overheads that support the teams working on the JROC activities. They represent an allocation rate of between 8% to 10% of overhead costs.
Updated forecasts will be provided monthly. Any unspent funds would be carried over into next six-month activity cycle or be transferred to the Interim Entity once established. The Budget covering the next funding period will of course take this into account.

## Slide 9: Financial Forecasts – Overall

## Slide 10: Financial Forecast - JROC Workstream costs
Chart: JROC Forecast (£)
| 45497 | 45528 | 45559 | 45589 | 45620 | 45650
WS1 | 6069.3333 | 7530.6667 | 9392 | 5882.6667 | 1400 | 1400
WS 2a | 4503 | 6080.3333 | 6080.3333 | 6528.3333 | 6089 | 6089
WS 2b | 3977 | 4133 | 5026 | 5026 | 8485 | 8485
WS 3 | 14565 | 24090 | 57210 | 48410 | 54855 | 28175
WS 4 | 3861.3333 | 3130.6667 | 4434.6667 | 6834.6667 | 1370 | 1370
WS 5 | 82810.8333 | 108568.5 | 146676 | 140576 | 237357 | 236237
WS 7 | 21685 | 20418.3333 | 21018.3333 | 20545 | 8220 | 8220
Chart: % Share of Total JROC Cost
| WS1 | WS 2a | WS 2b | WS 3 | WS 4 | WS 5 | WS 7
 | 0.022579 | 0.025214 | 0.025044 | 0.16203 | 0.014971 | 0.6788 | 0.071361

## Slide 11: Plan on a page

## Slide 12: DRAFT JROC Workstreams Consolidated POAP – 25/07/24
Workstream Substream | Work Packages | 2024 |  |  |  |  |  |  | 2025 |  |  |  |  | 
Workstream Substream | Description | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Q2 | Q3 | Q4
Governance |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1. Levelling up | API Availability & Performance |  |  |  |  |  |  |  |  |  |  |  |  | 
2a. Financial Crime Data | Fraud Data |  |  |  |  |  |  |  |  |  |  |  |  | 
2b. Financial crime tools (TRIs) | TRI Pilot – Phase 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
3. Consumer Protection | Gap Analysis |  |  |  |  |  |  |  |  |  |  |  |  | 
4. Information Flows | Open Banking Standard |  |  |  |  |  |  |  |  |  |  |  |  | 
 | FCA work package Confirm next steps |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Pay.uk work package Recommendation 3: Payment system changes to support clarity of payment status |  |  |  |  |  |  |  |  |  |  |  |  | 
5. Commercial VRPs |  |  |  |  |  |  |  |  |  |  |  |  |  | 
12
Publish 6mth Summary of Data Report to JROC
Publish analysis & recommended next steps to JROC
Publish Open Banking Standard v4.0
Standard
Refer to detailed substream plan for further details
Monitor adoption of voluntary implementation
Publish 6mth Summary of Fraud Data Report to JROC
Publish Initial Conclusions Report to Ecosystem
FCA led review and decision on next steps
Pay.uk publish report to JROC
Publish Consumer Gaps Recommendation Report to JROC
Produce Report
Roundtables
Scope doc
Readiness
KEY | 
WGC | Working Group consultation
IC | Industry consultation
 | Priority activity milestone
TPP Engagement
Publish TRI Recommendations Report to JROC
Finalise Report
Volume ramp up
Monitor / Analysis
Draft
Incremental progress updates shared with FCA/JROC
DEP - Report to inform
SS5 MLA Development
H/L Pilot outcomes report shared with FCA
Data Collection
Analysis
Analysis
Data Collection
ASPSP Engagement
Publish report to JROC on ASPSP feedback
If sufficient data received
If sufficient data received
Roundtables
Initial findings report shared with FCA/JROC
Publish report to JROC on TPP feedback
Pay.uk to define plan and interim delivery milestones
Timings yet to be agreed
Publish update on
adoption to FCA/JROC
Interim data collection status update shared with FCA/JROC / validation of feasible end date based on participant submissions
Internal OBL checkpoint updates
Initial findings report shared with FCA/JROC
Interim data collection status update shared with FCA/JROC
Roundtables
Internal OBL checkpoint updates
Data collection with sufficient levels of data has not yet been realised
Data collection with sufficient levels of data has not yet been realised
Publish Scope Doc to JROC
Publish Initial findings to JROC

## Slide 13: DRAFT JROC Workstream 5 POAP – 25/07/24
Workstream Substream | Work Packages | 2024 |  |  |  |  |  |  | 2025 |  |  |  |  | 
Workstream Substream | Description | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Q2 | Q3 | Q4
Governance |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5.1. Technical | Requirements |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Blueprint Action Plan |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Rollout Guidelines |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Wave 1 Success Criteria |  |  |  |  |  |  |  |  |  |  |  |  | 
 | LT Tech/Functional Roadmap |  |  |  |  |  |  |  |  |  |  |  |  | 
5.2. Disputes | Dispute system requirements (functional & non-functional) |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Dispute System for Wave 1* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Disputes Framework |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Sector definitions for Wave 2+ |  |  |  |  |  |  |  |  |  |  |  |  | 
5.3. Industry | Participant Readiness and Engagement |  |  |  |  |  |  |  |  |  |  |  |  | 
5.4a. MLA Dev | Procure External Legal Support* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Sector definitions for Wave 1 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Development of MLA v1.0* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | MLA / Disputes operating model* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | MLA Roadmap |  |  |  |  |  |  |  |  |  |  |  |  | 
5.4b. Commercial Framework |  |  |  |  |  |  |  |  |  |  |  |  |  | 
13
PLACEHOLDER - JROC approval
Publish Wave 1 readiness report to JROC
Wave 1 Success Criteria agreed and signed-off
Publish Final Dispute system functional & non-functional requirements for Wave 1
WGC
Iterative draft cycles
Approval & publication of Rollout Guidelines
Onboard external law firm support for MLA
PLACEHOLDER - JROC decision on approach to follow for the procurement of external legal support
WGC
Update
Draft Op Model
Approval & publication of MLA operating model
Approval & publication of Disputes Framework
Level, nature, and duration of OBL activities required TBC once PSR decision made
PLACEHOLDER - JROC decision on the commercial model
Placeholder schedule
Define
Refine
MLA full Bus Reqs finalised
IC
Baseline plan
Develop Phase 1 Delivery Plan
WG’s in place (fortnightly cadence)
Establish & run VRP Working Groups
Draft
Comprehensive progress update on WS5 to JROC (PSR)
Publish OB Standard v4.0
Standard
Draft
WGC
Draft 2
PLACEHOLDER - Start of Wave 1 – date TBC
Approval of Draft LTR
Publish Draft for industry consultation
* Appointment of a delivery lead has yet to be determined by JROC, plan predicated on assumption OBL will be selected. In the event of an alternative decision being taken, further planning will be required.
** Illustrative duration – actual timeframe will be instructed by the Regulators.
12
Ongoing alignment to the Disputes Framework
Define Eval criteria
Deep dive of leading solutions
Update / sign-off
Draft
WGC
Draft 2
09
13
08
JROC Board
04
JROC non-Order Programme Implementation Group
02
06
04
01
18
Funders Advisory Panel
08
09
04
Fin Com
20
24
22
19
19
VRP Implementation Group
31
28
25
30
20
17
VRP Working Group
12
25
08
05
19
03
17
31
14
28
12
26
Approval of MLA Roadmap
Requirements / analysis
Draft
Continued activities to further advance the MLA for Waves 2 & 3
Approval & publication of MLA v1.0
Update
Publish Guidance Notes
Sign-up phase**
Readiness / Build phase**
OBL providing support in the rollout of the MLA
Readiness
Propositional Bus Reqs defined
Approval of Final Draft of Rollout Guidelines
Approval of Final Draft of Disputes Framework
Approval of MLA final draft for broader IC
Updates if required
Updates if required
2025 governance forums and cadence to be defined
Evolve in readiness for Waves 2 & 3
Evolve in readiness for Waves 2 & 3
Illustrative timeline
KEY | 
WGC | Working Group consultation
IC | Industry consultation
 | Priority activity milestone
Wave 2 draft requirements agreed
Eval potential solutions
Procurement process
Evaluation of
MLA Operators
Business
Requirements
Define
Refine
Finalise operational business reqs
JROC approval of MLA Operator
Updates if required
Approval of Final
Draft of MLA Op Model
Publish sector definitions for Wave 1
Monitor and maintain up-to-date list of ASPSPs & TPPs
'expressions of interest’ and readiness​
JROC approve Dispute solution
Blueprint recommendations analysis published to Working & Coordination Groups
DEP - Report to inform
SS5 MLA Development
Placeholder - alternative solution to be identified – design/build/test/implement activities to be considered
Define and implement arbitration approach and solution
11
Wave 1 Readiness Report
WGC
Draft
WGC
Draft 2 / sign-off
Draft
Longer-term
Roadmap
Iterative drafts shared with VRP PIG
Draft Wave 2 requirements
Illustrative delivery schedule if the Salesforce
solution is recommended (ASSUMPTION)
Core build complete ready for UAT
Wave 1 Disputes solution ready for go-live
UAT/release readiness
H/L & user story design
Build & QA
WGC
Draft 2 / sign-off
Draft
Roundtables
Readiness
Define and develop Wave 2 definitions (timings TBC)
Advisory Group sessions with broader ecosystem
Socialisation
Implementation by ecosystem
Timings to be confirmed

## Slide 14: Programme status update

## Slide 15: Workstreams 1-4 Status Report (as at 26.07.24)
Workstream | RAG Status |  |  |  | Key Progress Updates | Upcoming Deliverables, Meetings and Focus Areas | Next week
 | Overall | Time | Quality | Risks | Include RAG rationale and action plan and any new risks or issues | Key Milestones/Deliverables due in next 4 weeks (as per plan) | Focus Areas for Next Period
1. Levelling up availability and performance | R | R | R | A | Reporting Red, to highlight the lack of confidence in the data available or expected to be received in time to support the workstream deliverables. OBL has processed data sub-missions since mid-Feb, as per plan, but low levels of participation and incomplete data. Requirement of 6 consecutive months of data for 60-80% of market not fulfilled, putting Nov deadline at risk TPP roundtable being organized on 01-Aug to mitigate the data risk and to help inform JROC on next steps, incl. potential FCA 'voluntary data request' | TPP roundtable scheduled for 01-Aug Questionnaire to be issued to participants to solicit feedback 01-16-Aug. Report to JROC on participants feedback planned for w/c 26-Aug. | TPP roundtable on 01-Aug. Draft and publish questionnaire. Continue collecting submission. Support participants.
2a. Financial Crime Data | A | R | A | A | Reporting Amber, noting a risk of not receiving substantive data in time to fulfil the workstream deliverables, however, confidence in expected data is higher than for WS1. OBL has processed data sub-missions since end-Feb, as per plan, but moderate participation (2 CMA9 + 1 non-CMA9) and incomplete data. Requirement of 6 consecutive months of data for 60-80% of market not fulfilled, potentially putting Nov deadline at risk ASPSP roundtable being organized on 1st Aug to mitigate the data risk and to help inform JROC on next steps, incl. potential FCA 'voluntary data request’. | ASPSP roundtable on 1st Aug. Questionnaire to be issued to participants to solicit feedback 01-16-Aug Report to JROC on participants feedback planned for w/c 26 Aug. | ASPSP roundtable on 01-Aug. Draft and publish questionnaire. Continue collecting submission Support participants
2b. Financial crime tools (e.g. TRIs) | A | A | A | G | Reporting Amber, to acknowledge the risk that the quality of data expected from participating ASPSP’s has not been established. TPPs are steadily raising TRI volumes; however, the total is still below expectations due to some caution now that we are ‘Live’. which is reflected as an amber status against the time measure. A forecasting tool has been set up to monitor anticipated volumes from TPPs, to help assess any potential impact on the pilot’s timeline and confirm the completeness of the TRIs being used. | Draft and publish incremental monthly (Aug/Sep) progress updates to FCA/JROC. | The focus on driving TRI volumes up and assessing the accuracy of the data provided; essential for a successful pilot. Monitor TPP volumes & TRI usage forecasts. Validate correct usage and accuracy of TRIs. The overall pilot activity from OBL will largely remain unchanged until we begin to see a significant increase in payment volumes sending TRIs, OBL will then start monitoring any changes and their impact.
3. Consumer Protection (Disputes) | G | G | A | G | Reporting Green. Held initial informal chat with FCA to discuss scope of next stages of WS3 To an extent there remains a lack of clarity on scope which needs to be addressed | Publish Scope Doc to JROC (Aug-24). Establish co-dependencies with WS5 consumer protection cross-cutting issues. | Progress thinking and finalise scope. Review scope internally and then share with FCA for input/sign-off. Set up/hold roundtables and develop stimulus materials.
4. Information Flows | G | G | G | G | Reporting Green. V4 of the OB Standard published in Jun-24 with information flow enhancements as optional, team will be monitoring adoption ahead of a publishing a report on status by the end of Sep-24. | Monthly bilats with ASPSPs to monitor adoption/implementation Discussion with Pay.uk regarding the development of FPS. | Deliver a 'gap analysis report' by end of Sep-24 sharing an ecosystem adoption/implementation status
RAG Definitions: | Overall (Based on Time, Quality and Risk RAGs) | Time/Schedule (on track to meet agreed deadlines) | Quality (confidence that the deliverables will meet JROC expectations) | Risks (risk to delivery)
Workstream RAG | This Week | Last Week
 | Overall | Overall
1. Levelling up | R | R
2a. Financial Crime Data | A | A
Workstream RAG | This Week | Last Week
 | Overall | Overall
2b. Financial crime tools | A | A
3. Consumer Protection | G | G
4. Information Flows | G | G

## Slide 16: Workstream 5 Status Report (as at 26.07.24)
Workstream |  | RAG Status |  |  |  | Key Progress Updates | Upcoming Deliverables, Meetings and Focus Areas | Next week
 |  | Overall | Time | Quality | Risks | Include RAG rationale and action plan and any new risks or issues | Key Milestones/Deliverables due in next 4 weeks (as per plan) | Focus Areas for Next Period
5.1. Technical |  | G | G | G | G | Reporting Green. Initial gap analysis and recommendations presented at the VRP WG 24-Aug. Agreed that no additional development of APIs required above sweeping (final feedback and confirmation pending from WG members). | Publish final (agreed) Blueprint recommendations analysis report Commence development of a technical requirements roadmap to support identified Wave 2/3 requirements. | Review any VRP WG feedback and update the Blueprint recommendation analysis report if required. Track technical and functional requirements that may arising from the MLA development substream.
5.2. Disputes |  | A | A | A | A | Reporting Amber due to the dependency on a JROC decision being made and the uncertainty of the delivery timings and requirements that may arise from that critical path decision. Working through the evaluation criteria of potential Dispute mechanisms/solutions with a key critical path dependency on a decision on what solution to take required by early September. Only the timing of the OBL solution has been assessed to-date so the viability of any alternative tool will need to be deep-dived, subject to the decision on which solution to adopt. | Publish final disputes system functional and non-functional requirements for Wave 1. Define evaluation criteria and framework including weighting. initial view of Disputes mechanism evaluation to be shared at VRP WG on 08-Aug. | Finalise the evaluation framework including weighting. Commence evaluation work to describe Dispute mechanisms/solutions.
5.3. Industry Engagement |  | G | G | G | G | Reporting Green. Tracker to collect TPP's 'expressions of interest' created – ongoing. Examples of potential cVRP use cases gathered from TPPs, to inform Policy work on sectors definition. | Update ‘expression of interest’ tracker. | Continue conversations with TPPs. Continue gathering potential use cases to inform Wave 1 sectors definition.
5.4. MLA & Commercial | 5.4a MLA | A | A | G | A | Reporting Amber due to the dependency on a decision being made on the procurement process in a timely manner and the risk that the subsequent activity plan may not be achieved in line with the current plan of record.. Business requirements have been split into 2 streams of work; proposition and operational requirements; have planned timetable of WG meetings to address. Need to start RFP process for legal support to meet agreed timelines, but do not have an agreed way forward with Pay.UK and JROC; propose to bring issue to VRP IG meeting on Jul-31 for a decision. | Publish the propositional business requirements for the MLA. To publish the Wave 1 sector definitions. To have selected and contracted with external legal firm ready for onboarding in early September. Establish co-dependencies with WS3 consumer protection cross-cutting issues. | Define and agree the Wave 1 sectors /use cases. Define and agree the propositional arrangements to be drafted into MLA clauses.
 | 5.4b Comm Framework | ON HOLD |  |  |  | Substream reported as on-hold because of the dependency on JROC's response to the call for views and clarity on the deliverables. Discussion with FCA and PSR on approach still required. | Define the deliverables required following review of the PSR’s consultation output. | To get better understanding of the regulatory vs OBL/Pay.UK proposed approach to getting a starting commercial rate
RAG Definitions: | Overall (Based on Time, Quality and Risk RAGs) | Time/Schedule (on track to meet agreed deadlines) | Quality (confidence that the deliverables will meet JROC expectations) | Risks (risk to delivery)
Workstream RAG | This Week | Last Week
 | Overall | Overall
5.1. Technical | G | G
5.2 Disputes | A | A
Workstream RAG | This Week | Last Week
 | Overall | Overall
5.3 Industry Engagement | G | G
5.4a MLA | A | A
5.4b Commercial Framework | ON HOLD | 

## Slide 17: Proposed Mitigating Actions
Table below shows the workstreams with either amber or red status with the causal factors and planned mitigations
Workstream | Causal factor(s) | Planned mitigations
WS1 – levelling up | Currently have limited reporting by firms, which means performance insights cannot be gathered which impedes the ability to identify and deliver a comprehensive dashboard on API performance/availability across the market. Hence, future improvements cannot be identified | Convene roundtables and workshops – starting on 1 Aug to obtain participant feedback on barriers to reporting. Outputs from the workshops will be analysed with a report to JROC by w/c 26 Aug
WS2a – financial crime data | Currently have data from 40% firms, which is insufficient to analyse the data and provide a summary of conclusions to ASPSPs to allow them to assess the efficacy of their fraud prevention tools and benchmark themselves against the wider industry | Convene roundtables and workshops – starting on 1 Aug to obtain participant feedback on barriers to reporting. Outputs from the workshops will be analysed with a report to JROC by w/c 26 Aug
WS2b – TRIs | Concerns around the quantity and quality of the performance analysis from participating ASPSPs which may not be sufficiently robust to allow comparisons and make firms conclusions on the efficacy of TRIs | Monitor supply of TRIs by TPPs and continue to encourage volume increase Continue to work closely with ASPSPs to understand TRI impact on performance
WS5.2 – VRP disputes | Reporting Amber due to the dependency on a JROC decision being made in relation to disputes mechanism and the knock-on uncertainty of the delivery timings and requirements that may arise from that critical path decision. | Undertaking analysis to review dispute mechanism options, which includes detailing business requirements and assessment criteria, as well as understanding more about the solution options. Aim is to provide an update to the VRPWG on 8 Aug and a final recommendation to VRPWG on 22 Aug. This will then be progressed through governance to the JROC Board for a final decision on 13 Sept Delivery timings of each option will be a core part of the initial analysis, which will then inform the ultimate delivery schedule
WS5.4 – VRP MLA | Reporting Amber due to the dependency on a decision being made on the procurement process in a timely manner and the risk that the subsequent activity plan may not be achieved in line with the current plan of record. Also, the lack of a commercial model, and a clear plan to identify this, is a risk to the delivery of the MLA | Tabled the legal support procurement approach at the VRP Implementation Group for agreement on the way forward Way forward for the commercial model is on the VRP Implementation Group agenda for discussion

## Slide 18: Governance update
Governance structure now in place with meetings now commencing
Funding firms representatives on Programme Workplan Implementation Group confirmed as Nationwide, Revolut, Experian and Truelayer
HSBC and Yapily to act as the ASPSP and TPP representatives on the Finance Committee
Claudio Pollack confirmed as the Chair of the Funders Advisory Panel
WS5 VRP has dual reporting lines, into both VRP Implementation Group and Programme Workplan Implementation Group. This reflects the complexity/nuances of the VRP delivery
Terms of reference for all the meetings have been created and are subject to final JROC approval
Finance Committee
JROC oversight & direction
Funders Advisory Panel
Workplan Implementation Group
JROC Board
VRP Implementation Group
WS 1 & 2
Levelling up
Fraud Data & Tools
WS5 VRP
Working Group
WS 3
Consumer protections

## Slide 19: Meetings summary
To date the following meetings have been held:
VRPWG – 12 July
Presented the high-level options for the VRP dispute mechanism and an overview of the evaluation approach to deciding which to take forward
Firms requested to provide feedback on the proposals by 26 July
VRP WG – 25 July
Presented an analysis of the MLA propositional elements, with a gap analysis between the model clauses and the VRP Blueprint recommendations. This suggested a number of themed gaps which will need addressing in the MLA
Firms requested to provide feedback on the gap analysis by 8 August
VRP IG – 31 July
Meeting focused on three key areas – baselining the VRP E2E plan, agreeing the approach for the procurement of legal support for the MLA development and how to progress the commercial model
Key topics for future meetings:
JWIG – 5 Aug
E2E workstream plan baseline
Procurement approach for MLA legal support
VRP WG – 8 Aug
Sector definitions for Wave 1
Dispute mechanism approach – initial findings and participant feedback
Functional gaps
JROC Board – 9 Aug
E2E plan and governance
Disputes functional requirements
Procurement approach for MLA legal support
Commercial model approach

## Slide 20: Procurement approach for MLA legal support

## Slide 21: Procurement approach for MLA legal support
Agreeing and commencing the procurement process for the legal support for the MLA development is a key element of the sub-stream two plan. The plan assumes that the procurement process is undertaken during August, which allows for a legal firm to be on-boarded by September to allow for drafting of the MLA. The procurement process itself is anticipated to take 4-5 weeks to complete. This decision is a core part of the sub-stream critical path :
Ideally the future scheme operator would take the procurement process forward, however this decision on the future scheme operator is unlikely to be made for some time. Hence there are a number of options on how to progress the procurement process:
Joint approach between Pay.UK and OBL
  Adopt a joint approach which is co-led by Pay.UK and OBL
  Requires agreement of a procurement approach which is acceptable to both organisations and aligns to the critical path
  Both are co-signatories to the contract and costs are split 50/50
OBL or Pay.UK to take the lead on the procurement process
  Would utilise the procurement process of the chosen organisation who would exclusively contract with the legal firm appointed
  Legal costs would be borne the appointing organisation. Note, OBL has budgeted for these costs in the current funding round
  Irrespective of which organisation is chosen as the lead the other organisation will be involved in the MLA development process
  Once the final scheme operator is chosen, they would take ownership of the MLA
The VRPIG has been asked to provide a view on how the procurement process should be undertaken to ensure a timely appointment which does not impact the plan timeline

## Slide 22: RFP Process to procure external legal support to develop MLA
Given the strategic importance of the VRP initiative and the large number of stakeholders who have a vested interest in the final work product (ie MLA 1.0), it's critical that we select a reputable and well-credentialed law firm with the right experience and capabilities to support this initiative
In accordance with our procurement policy, [OBL/Pay.UK] will design and run an RFP process to allow us to select a preferred law firm provider to develop a modular-style MLA contract template
While the RFP process typically takes a few months to design and run, in this case, we propose to run a concise process during the month of August. By end of August, we intend to:
  evaluate proposals from respondents against defined criteria, and
  select, negotiate and agree the terms of a contract with a preferred supplier
A detailed 'Brief to Counsel' will be included in the RFP documentation setting out detailed instructions around:
  Background/purpose, scope, drafting principles (eg ensuring rights and interests of consumers and participants are properly safeguarded and covered), business requirements (proposition and operational) to be factored in
  Outcomes and deliverables to be produced, timelines/milestones to meet, and ways of working
  Project governance (eg roles and responsibilities, style/approach to drafting, meeting cadence, billing requirements, etc)
Aim is to have an MLA 1.0 ready for industry consultation by end of December/early January. So, it's vital that we run the RFP process now and to complete that process by end of August to enable the drafting work to produce MLA 1.0 to begin in early September
Early engagement of law firm supplier means they can be included in critical VRP WG meetings, enabling them to better understand the purpose, scope and business & structural requirements for the MLA. This ensures the MLA contract aligns with the business and operational requirements for the commercial VRP product

## Slide 23: There are several potential dimensions for the assessment of a preferred option
Option | Advantages | Risks
Joint approach between Pay.UK and OBL | Aligned to JV approach to shared costs & governance Mitigates risks of excluding issues that are relevant to the ultimate MLA operator Allows the deferment of MLA operator choice which may be better informed when the MLA itself is better evolved/ is a strategically important decision that requires careful consideration. Allows deferral of any sub-contracting requirement between MLA owner and Dispute system provider until later in the process when a decision on the optimal disputes mechanism is due. | Complicates the procurement process due to differing procurement policies across each organisation. Joint contract with a firm introduces additional administrative complexity. No obvious solution to effectively resolve any differences in views that may emerge in the process (including OBL funders). Introduces the risk of potential delays if a joint decision becomes difficult to achieve.
OBL or Pay.UK to take the lead on the procurement process | Less complex approach with sole accountability for decision making Better position to evaluate any specific needs of the ultimate MLA operator within the process. May be more administratively simple and facilitate a quicker decision Easier and quicker to define relevant selection evaluation criteria Easier to hold the supplier to account for performance and deliverables. | The ultimate chosen MLA operator is distant from the process This results in rework delaying the finalisation of the MLA and additive costs Potential misallocation of costs to the wrong funding pool

## Slide 24: Broader WS 5 workplan overview

## Slide 25: Non-Sweeping VRP Workstreams and Deliverables
SS2 Disputes
Designing and implementing a disputes framework and mechanism as required for Wave 1
Review of customer protection gaps for Wave 2+*
SS3 Industry Coordination
Sector definition by wave.
Coordination across industry to ensure good levels of rollout participation, onboard participants and work with them bilaterally / collectively to resolve issues.
SS4 MLA
Creation of MLA for Wave 1, building on Model Clauses work
Defining an outline, sustainable commercial framework for Waves 1+
SS1 Technical & Function
All technical requirements for Wave 1, including additional operational / CX guidance and the measurement of outcomes
Longer term technical / functional roadmap to support Waves 2+
Delivery by Dec 2024
Fulfilment of all technical requirements for Wave 1
Development of long-term technical and functional roadmap to support Waves 2+
Development of Disputes Framework for Wave 1
Development of fit for purpose Disputes Mechanism for Wave 1
Definition of protection gap and consideration of options for Wave 2+*
Clear definition of in scope sectors for Wave 1+
Extensive engagement across ecosystem
Expressions of interest
MLA 1.0 in draft form, ready for consultation
Commercial Framework evaluation complete and ready for broader industry consultation
Delivery approach: all deliverables developed through extensive industry engagement via Steering Group / Working Groups / Advisory Groups / Consultation and with close regulatory oversight

## Slide 26: SS1 Technical and Functional – Overview
Why is this important for the Non-Sweeping VRP Rollout?
As per the JROC Response to the VRP Blueprint: “The blueprint contains over 65 actions that, in the view of the Working Group, would be needed to enable the first phase of VRP services, as well as those that would be needed to support wider services in future.”
To deliver a high-quality roll-out, all necessary technical and functional requirements must be in place and implemented. Aim to satisfy the recommendations and requirements identified by the Blueprint and identified by OBL as necessary for Wave 1.
Key Questions to Answer
For each Blueprint recommendation, to what extent are these already required under existing regulations and legislation?
For each Blueprint recommendation, to what extent is it addressed by the UKF model clauses?
Where are the ‘gaps’ in satisfying recommendations?
How do we plan on closing those gaps, and what actions are required? E.g. additional MLA clauses, future standards updates etc.
Does the FPS pricing have to change?
What will the Sub-Stream Produce? (Bold = Artefacts)
A Wave 1 Tech / Functional Report that confirms all necessary VRP Blueprint pre-pilot and pilot recommendations, JROC response recommendations and other OBL identified necessary actions are satisfied within this sub-stream or other sub-streams.
Rollout Guidelines, to complement the MLA (eg, to include recommended CX)
Data gathering and reporting method (to be included in Rollout Guidelines).
Longer-term technical/functional roadmap (e.g. Standards updates not required for Wave 1 which are needed for future waves).
Notes
Assumptions: Provisional analysis is that technical and functional readiness can be achieved without updates to the Open Banking Standards prior to Wave 1, with prescriptive model clauses where necessary.
Scope: Technical and functional readiness for Wave 1, and the pre-pilot and pilot recommendations in the Blueprint. Post-pilot recommendations, and longer-term technical/functional improvements will be captured in a longer-term roadmap.

## Slide 27: SS2 Disputes – Overview
Why is this important for the Non-Sweeping VRP Rollout?
As per the JROC Response to the VRP Blueprint: “Existing requirements are largely sufficient to cover an initial rollout … but … a number of enhancements could be made… This includes the creation of a formal dispute resolution mechanism”.
All parties need to be clear who bears liability when something goes wrong, any grey areas need to be clarified, and there needs to be a simple process to enable the sharing of information and assigning liability to another party to ensure that consumers do not suffer poor outcomes.
Key Questions to Answer
What are the potential things that can go wrong with a Non-Sweeping VRP (“Unhappy Paths”)
What is the regulatory and legal position on each “unhappy path”?
Who is liable under each “unhappy path”?
What system is needed to help participants communicate and assign liability to each other?
How is liability assigned if participants cannot agree?
What will the Sub-Stream Produce? (Bold = Artefacts)
A list of Unhappy Paths, drawing on learnings from VRP for Sweeping
A summary of the regulatory position for each unhappy path, the position in the MLA (when complete) and obligations on all participants (the Disputes Framework)
Requirements for a Dispute Resolution Mechanism (Artefact 3: Requirements)
An evaluation of potential solutions that can meet the requirements
Creation of a W1 Dispute Resolution Mechanism.
Design and implementation of an Arbitration System, undertaken by the MLA Operator
Notes
Assumptions: The timing plan assumes that a relatively simple solution emerges as the preferred option for the mechanism. If a decision is taken to develop a brand new solution or contract with a third party to supply, timings are unknown.
Scope: As per the VRP Blueprint and JROC Response, this assumes there will be no additional purchase protection for Wave 1. Consideration of when additional purchase protection will be provided, its scope, process and mechanism requirements will be considered urgently under WS3.

## Slide 28: SS3 Industry Coordination – Overview
Why is this important for the Non-Sweeping VRP Rollout?
The non-Sweeping VRP Rollout requires the effective communication, education and co-ordination of all participants. In particular, from experience of previous roll-outs, we know that the interaction between TPPs, Billers / Merchants, Sending Banks and OBL is of particular importance to ensure high-quality roll-out and address issues promptly. The complexity of this Rollout requires close engagement with industry. Essentially this is the pilot execution sub-stream.
Key Questions to Answer
Which sectors will form part of each Wave of Rollout?
Building from the high-level sector definitions in the VRP Blueprint, which types of business are in scope of Wave 1?
Which firms could be early adopters of non-Sweeping VRP?
What will the Sub-Stream Produce? (Bold = Artefacts)
A set of precise sector definitions to clarify exactly which firms are in scope of Wave 1
From market engagement, sector prioritization an identification of sectors with greatest interest in non-Sweeping VRP rollout?
As we approach Rollout, a list of interested parties (ASPSPs, TPPs, Billers) and tracking their rollout readiness
Engagement structure to support participants as they go live with Wave 1 and beyond
Notes
Assumptions: Engagement with participants will ramp up once there is greater clarity on commercials, sectors in scope, timing and phasing of Rollout.

## Slide 29: SS 4a MLA Drafting – Overview
Why is this important for the VRP Rollout?
As per the JROC Response to the VRP Blueprint: “on evidence currently available to us, we consider there is a need for a multilateral agreement between PISPs and sending firms … to enable easier market access to participants and limit the cost and inefficiencies from bilateral arrangements”.
This sub-workstream is drafting, consulting and ultimately agreeing the MLA(s) which will be used to launch Wave 1 and later iterations of waves 2 and 3, and into steady state.
Key Questions to Answer
Which organisation will operate the MLA?
What are the business requirements of the MLA e.g.
  Access criteria to sign up to the MLA
  PISP requirements on which billers can be signed up
  Operator fees
  Settlement of any money wrt liability
Policy related decisions on what rules and standards apply e.g. mandatory TRIs, mandatory consumer messaging.
Interaction with underlying payment system rules: FPS & CHAPS.
What will the Sub-Stream Produce? (Bold = Artefacts)
A list of business rules
A list of policy choices, to ensure the MLA best reflects the needs of consumers, billers, TPPs, ASPSPs and Regulators.
RFP and Instructions to counsel
Draft MLA(s) and consultation
Final MLA 1.0
Future iterations of MLA(s) 2.0 and 3.0
Notes
Assumptions: The MLA will be written as a standalone, as much as is possible, to be able to be operated by a third party and apply to any credit payment system. We assume this is possible and still meet certain legal requirements. We also assume that when implemented it is a voluntary commitment between parties rather than legislated via the process of revoking PSRs 2017 or by FCA rules or PSR directions.
Scope: As per the VRP Blueprint and JROC Response, this needs to be in place to make the market work; the scope is to build out from the basics of MLA 1.0 (low risk billers with no commercial model and no purchase protections) through to MLA 3.0 which opens up to more risky sectors but with those other elements in place.

## Slide 30: Sub-workstream 4b Commercial Model / Black Box – Overview
Why is this important for the Non-Sweeping VRP Rollout?
As part of the Blueprint work and MLA is was always anticipated that Non-Sweeping VRPs would provide a commercial return between the PISPs and ASPSPs that signed up. This workstream proposes objectively defining a rate card for Non-Sweeping VRP as covered by MLA 2.0 and MLA 3.0.
Key Questions to Answer
What learnings can we take on how to set prices in an emerging market where a product doesn’t exist yet?
What levels of rate card are needed to stimulate a new and emerging market rather than a mature market?
How to implement a rate card review process to address changes between emerging and maturing markets?
What needs to be implemented in MLA 2.0 and how will it be operationalised?
What will the Sub-Stream Produce? (Bold = Artefacts)
A review of different price setting mechanism
A black box rate card for MLA 2.0
Operational clauses for implementation in MLA 2.0
Recommendations for moving beyond black box after moving from emerging market to a maturing one; to be adopted at a later date.
Notes
Assumptions: We are expecting to appoint an external consultancy to undertake the work, having agreed with the relevant WG, SG on the proposed approach to setting a starting rate card. We have to assume there is a credible consultancy and that ASPSPs and PISPs will work with them as per any information requirements. We also assume the external consultancy can be onboarded and conduct the work to the expected time frames.
Scope: Planning on a consultation at the same time as the MLA 1.0 consultation – for adoption in MLA 2.0 and to give clear direction of travel for participants.

## Slide 31: AOB