## Slide 1: JROC non-Order Programme Workplan Implementation Group
9 September 2024
Produced by: OBL
Classification: CONFIDENTIAL

## Slide 2: Housekeeping Items
Virtual Meeting Etiquette:
Please turn on your camera if possible and please turn off your mic when you are not speaking. Please kindly raise your 'virtual hand' if you would like to speak, and state your affiliation first, or you can type your questions in Chat.
Competition Law:
Many of you are from competitor organisations. As you will be aware it is critical that we all comply with competition law. If you are in any doubt about competition law compliance you should consult your compliance team.
The discussions between the attendees should be limited to discussing issues of general concern and you must not share or discuss any information that is commercially sensitive and not in the public domain – that includes: current or future prices, strategies, matters about customers or suppliers.
You can and should share your expertise about the matters that are specific to today’s agenda and can talk about matters that are public.
If any topic is raised which you feel uncomfortable discussing, please make this known and we will immediately adjourn discussions on that point.

## Slide 3: Agenda
Minutes of last meeting
Plan on a page
Programme status update
Disputes mechanism recommendation
MLA operator decision approach
Wave 1 sector definition
Workstream 1 and 2 update
Workstream 2b change request – pilot extension
Procurement approach for MLA legal support – update
AOB

## Slide 4: 1. Minutes from last meeting
Classification: CONFIDENTIAL
4

## Slide 5: 2. Plan on a page
Classification: CONFIDENTIAL
5

## Slide 6: JROC Programme POAP – 15/08/24 v1.0
Workstream Substream | Work Packages | 2024 |  |  |  |  |  |  | 2025 |  |  |  |  | 
Workstream Substream | Description | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Q2 | Q3 | Q4
Governance |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1. Levelling up | API Availability & Performance |  |  |  |  |  |  |  |  |  |  |  |  | 
2a. Financial Crime Data | Fraud Data |  |  |  |  |  |  |  |  |  |  |  |  | 
2b. Financial crime tools (TRIs) | TRI Pilot – Phase 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
3. Consumer Protection | Gap Analysis |  |  |  |  |  |  |  |  |  |  |  |  | 
4. Information Flows | Open Banking Standard |  |  |  |  |  |  |  |  |  |  |  |  | 
 | FCA work package Confirm next steps |  |  |  |  |  |  |  |  |  |  |  |  | 
5. Commercial VRPs |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6
Publish 6mth Summary of Data Report to JROC
Publish analysis & recommended next steps to JROC
Publish Open Banking Standard v4.0
Standard
Refer to detailed substream plan for further details
Monitor adoption of voluntary implementation
Publish 6mth Summary of Fraud Data Report to JROC
Publish Initial Conclusions Report to Ecosystem
FCA led review and decision on next steps
KEY | 
WGC | Working Group consultation
IC | Industry consultation
 | Priority activity milestone
TPP Engagement
Publish TRI Recommendations Report to JROC
Finalise Report
Volume ramp up
Monitor / Analysis
Draft
Incremental progress updates shared with FCA/JROC
H/L Pilot outcomes report shared with FCA
Data Collection
Analysis
Analysis
Data Collection
ASPSP Engagement
Publish report to JROC on ASPSP feedback
If sufficient data received
If sufficient data received
Roundtables
Initial findings report shared with FCA/JROC
Publish report to JROC on TPP feedback
Timings yet to be agreed
Publish update on
adoption to FCA/JROC
Interim data collection status update shared with FCA/JROC / validation of feasible end date based on participant submissions
Internal OBL checkpoint updates
Initial findings report shared with FCA/JROC
Interim data collection status update shared with FCA/JROC
Roundtables
Internal OBL checkpoint updates
Data collection with sufficient levels of data has not yet been realised
Data collection with sufficient levels of data has not yet been realised
DEP - Report to inform 5.4A MLA Development
Publish Consumer Gaps Recommendation Report to JROC
Produce Report
Preparation
Scope doc
Publish Initial findings to JROC
OBL to pilot a dash-board of API RAG rating and API for data collection
OBL to deliver an analysis on API performance and availability data
Present a report to JROC on outcomes, conclusions and recommended next steps

## Slide 7: JROC Programme - Workstream 5 POAP – 15/08/24 v1.0
Workstream Substream | Work Packages | 2024 |  |  |  |  |  |  | 2025 |  |  |  |  | 
Workstream Substream | Description | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Q2 | Q3 | Q4
Governance |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5.1. Technical | Requirements |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Blueprint Action Plan |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Rollout Guidelines |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Mi Requirements |  |  |  |  |  |  |  |  |  |  |  |  | 
 | LT Tech/Functional Roadmap |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Wave 1 / Pilot Go Live Criteria |  |  |  |  |  |  |  |  |  |  |  |  | 
5.2. Disputes | Dispute system requirements (functional & non-functional) |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Dispute System for Wave 1* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Disputes Framework |  |  |  |  |  |  |  |  |  |  |  |  | 
5.3. Industry | Participant Readiness and Engagement |  |  |  |  |  |  |  |  |  |  |  |  | 
5.4a. MLA Dev | Procure External Legal Support* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Sector Definitions - Waves 1 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Development of MLA v1.0* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | MLA / Disputes Operating Model* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | MLA Roadmap Development |  |  |  |  |  |  |  |  |  |  |  |  | 
5.4b. Commercial Framework |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7
PLACEHOLDER – FCA/PSR approval
Publish Wave 1 readiness report to JROC
MI requirements agreed and signed-off
Publish Final Dispute system functional & non-functional requirements for Wave 1
WGC
Iterative draft cycles
Approval & publication of Rollout Guidelines
Onboard external law firm support for MLA
FCA/PSR decision on approach to follow for the procurement of external legal support
WGC
Update
Draft Op Model
Approval & publication of MLA operating model
Approval & publication of Disputes Framework
Level, nature, and duration of OBL activities required TBC once PSR decision made
PLACEHOLDER – FCA/PSR decision on the commercial model
Placeholder schedule
Define
Refine
MLA full Bus Reqs finalised
IC
Baseline plan
Develop Phase 1 Delivery Plan
WG’s in place (fortnightly cadence)
Establish & run VRP Working Groups
Draft
Comprehensive progress update on WS5 to JROC (PSR)
Publish OB Standard v4.0
Standard
Draft
WGC
Draft 2
PLACEHOLDER - Start of Wave 1 – date TBC
Approval of Draft LTR
Publish Draft for industry consultation
* Appointment of a delivery lead has yet to be determined by JROC, plan predicated on assumption OBL will be selected. In the event of an alternative decision being taken, further planning will be required.
** Illustrative duration – actual timeframe will be instructed by the Regulators.
12
Ongoing alignment to the Disputes Framework
Define Eval criteria
Deep dive of leading solutions
Update / sign-off
Draft
WGC
Draft 2
09
13
07
JROC Board
04
JROC non-Order Programme Implementation Group
02
06
04
01
18
Funders Advisory Panel
08
09
04
Fin Com
15
24
22
19
19
VRP Implementation Group
31
28
25
30
20
17
VRP Working Group
12
25
08
05
19
03
17
31
14
28
12
26
Approval of MLA Roadmap
Requirements / analysis
Draft
Continued activities to further advance the MLA for Waves 2 & 3
Approval & publication of MLA v1.0
Update
Publish Guidance Notes
Sign-up phase**
Readiness / Build phase**
OBL providing support in the rollout of the MLA
Readiness
Propositional Bus Reqs defined
Approval of Final Draft of Rollout Guidelines
Approval of Final Draft of Disputes Framework
Approval of MLA final draft for broader IC
Updates if required
Updates if required
2025 governance forums and cadence to be defined
Evolve in readiness for Waves 2 & 3
Evolve in readiness for Waves 2 & 3
Illustrative timeline
KEY | 
WGC | Working Group consultation
IC | Industry consultation
 | Priority activity milestone
Wave 2 draft requirements agreed
Eval potential solutions
Procurement process
Evaluation of
MLA Operators
Business
Requirements
Define
Refine
Finalise operational business reqs
Approval of MLA Operator
Updates if required
Approval of Final
Draft of MLA Op Model
Publish sector definitions for Wave 1
Monitor and maintain up-to-date list of ASPSPs & TPPs
'expressions of interest’ and readiness​
JROC approve Dispute solution
Blueprint recommendations analysis published to VRPWG
DEP - Report to inform
SS5 MLA Development
Placeholder - alternative solution to be identified – design/build/test/implement activities to be considered
Define and implement arbitration approach and solution
07
Wave 1 Readiness
Report
WGC
Draft
WGC
Draft 2 / sign-off
Draft
Longer-term
Roadmap (LTR)
Iterative drafts shared with VRP PIG
Draft Wave 2 requirements
Illustrative delivery schedule if the Salesforce
solution is recommended (ASSUMPTION)
Core build complete ready for UAT
Wave 1 Disputes solution ready for go-live
UAT/release readiness
H/L & user story design
Build & QA
WGC
Draft 2 / sign-off
Draft
Roundtables
Readiness
MLA Roadmap Development (Inc. Wave 2+ Definitions) (timings TBC)
Advisory Group sessions with broader ecosystem
Socialisation
Implementation by ecosystem
Timings to be confirmed
Interim updates shared with VRPWG
PSR - Proposed commercial models presented for sign off
FCA - Additional premium APIs identified and presented to JROC with a recommendation as to which to progress in this workstream
Publish Wave 1 / Pilot Go Live Criteria
Draft
WGC
Draft 2

## Slide 8: 3. Programme status update
Classification: CONFIDENTIAL
8

## Slide 9: JROC Executive Exceptions Report (as at 30.08.24)
Previous: | Amber | Current: | Amber
The final recommendation on the VRP dispute mechanism solution will be going to the JROC Board on the 13th September, at which point the workstream should turn green. A change request in relation to the MLA operator was approved by the VRP IG on 28th August with a recommendation to go to the JROC Board on the 7th November. Activities are now underway to complete the evaluation. The MLA RFP process is still being progressed with a decision anticipated by the end of this week. We have successfully delivered the WS1 and WS2a reports to JROC and are now awaiting feedback. A change request will be going to the JWIG on 9th September to extend the pilot for 2b, the November date is still on track. VRP WG and Funders Advisory Panel scheduled for 5th and 6th September, respectively. |  |  | 
WS1 Levelling Up |  | ó |  | November deadline at significant risk due to low volume and low-quality data
WS2a Financial Crime Data |  | ó |  | November deadline at some risk due to low volume and low-quality data
Ws2b Financial Crime Tools (TRIs) |  |  |  | TPPs have not been pushing through enough TRI data which will mean pilot end date will need to be extended
WS3 Consumer Protection, (Disputes) |  | ó |  | On Track
WS4 Information Flows |  | ó |  | On Track
WS5.1 Technical |  | ó |  | On Track
WS5.2 Disputes |  | ó |  | Current plan remains very tight. Recommendation on disputes system made. Awaiting final feedback.
WS5.3 Industry Engagement |  | ó |  | On Track
WS5.4a MLA |  | ó |  | On Track
WS5.4b Commercial Framework |  | ó |  | On Hold
Workstream RAG Status Exec Summary
Workstream and RAG |  | Reason for Non-Green Status |  | Action Plan |  | Action Owner |  | Action Target Completion Date |  | Status
WS1 Levelling Up |  | Reporting Red due to lack of confidence in the data available or expected to be received in time to support the workstream deliverables. |  | Hold TPP & ASPSP roundtables to understand blockers in providing data and to help inform JROC on next steps, incl. potential FCA 'voluntary data request’. Issue surveys to TPPs and ASPSPs sent to 22 TPPs, with a 15/08 deadline Analyse feedback from roundtables and surveys and produce an Ecosystem feedback summary report to JROC JROC to review report and to decide to proceed with a mandatory or voluntary data request |  | OBL OBL OBL JROC |  | 01/08/24 01/08/24 30/08/24 TBC |  | Complete Complete Complete Open
WS2a Financial Crime Data |  | Reporting Amber as there is a risk of not receiving substantive data in time to fulfil the workstream deliverables, however, confidence in expected data is higher than for WS1. |  |  |  |  |  |  |  | 
Ws2b Financial Crime Tools |  | Reporting Amber as there were issues with the volume, range and consistency of TRIs sent by TPPs to ASPSPs. Banks have highlighted they will not be able to complete robust efficacy analysis by the end of Sep. |  | Fix data provision issues with TPP’s Extend pilot period to end October and truncate evaluation period, (no impact on critical milestone) Work closely with TPPs and ASPSPs to ensure that this extended time period is sufficient to enable robust analysis to be undertaken |  | OBL JWIG OBL |  | 30/08/24 09/09/24 30/10/24 | O | Complete Open Open
WS5.2 Disputes |  | Reporting Amber due to tight timelines and potential need for re-plan. Although trending green as we are comfortable that the final decision on the disputes system will confirm the recommendation. |  | Complete options analysis of dispute tools and produce proposals for JROC decision on tool, operator, etc JROC decisions on the choice of dispute tool solution & operator & arbitration approach, solution, & operator. Replanning activities to align and update the delivery plan with the JROC decisions made on the 13/09. |  | OBL JROC OBL |  | 22/08/24 13/09/24 30/09/24 |  | Complete Open Open
Non-Green Return to Green Plan
Workstream |  | Decision Required |  | JROC Decision Date |  | Decision Status |  | Decision Outcome |  | Date of Decision
Levelling Up |  | Checkpoint for JROC to determine next steps to increase the data to complete an effective evaluation |  | 13/09/24 |  | Open |  | TBC |  | TBC
Financial Crime Data |  |  |  |  |  |  |  |  |  | 
Disputes |  | Decision on the dispute tool solution. Decision on the operator of the (agreed) dispute tool solution. Decision on the dispute arbitration approach, solution, and operator. |  | 13/09/24 07/11/24 07/11/24 |  | Open Open Open |  | TBC |  | TBC
MLA |  | Choice of operator for the MLA. Decision on whether the MLA and Disputes Operator needs to be the same. Subject to PSR consultation, what the role of the MLA operator will be in the commercial framework development. Determine the commercial framework (price clause) for inclusion in the MLA for Wave 1. |  | 07/11/24 07/11/24 TBC TBC |  | Open Open Open Open |  | TBC |  | TBC
JROC Decision Log
JROC Programme Delivery Headline Summary

## Slide 10: Workstreams 1-4 Status Report (as at 30.08.24)
RAG Definitions: | Overall (Based on Time, Quality and Risk RAGs) | Time/Schedule (on track to meet agreed deadlines) | Quality (confidence that the deliverables will meet JROC expectations) | Risks (risk to delivery)
Workstream RAG | This Week | Last Week
 | Overall | Overall
1. Levelling up | R | R
2a. Financial Crime Data | A | A
Workstream RAG | This Week | Last Week
 | Overall | Overall
2b. Financial crime tools | A | G
3. Consumer Protection | G | G
4. Information Flows | G | G
Workstream | RAG Status* |  |  |  | Key Progress Updates | Upcoming Deliverables, Meetings and Focus Areas | Next week
 | Overall | Time | Quality | Risks | Include RAG rationale and action plan and any new risks or issues | Key Milestones/Deliverables due in next 4 weeks (as per plan) | Focus Areas for Next Period
1. Levelling up availability and performance | R | R | R | A | Reporting Red, to highlight the lack of confidence in the data available or expected to be received in time to support the workstream deliverables. OBL has processed data submissions since mid-Feb, as per plan, but low levels of participation and incomplete data observed. Requirement of 6 consecutive months of data for 60-80% of market not fulfilled, putting Nov deadline at risk. TPP roundtable organized 1st August and questionnaire sent that same day. 18 responses received by 15/08 deadline (78% of those contacted). Early summary of responses provided to JROC on 19/08. Full report sent to JROC on 30/08. | Final report to JROC on TPP/ASPSP’. responses to the Questionnaires by 30/08- Complete. JROC decision on next steps, once reports are issued. | Support participants with any MI questions. Working with JROC on next steps relating to voluntary data request
2a. Financial Crime Data | A | A | R | A | Reporting Amber, noting a risk of not receiving substantive data in time to fulfil the workstream deliverables, however, confidence in expected data is higher than for WS1. OBL has processed data submissions since end-Feb, as per plan, but moderate participation (2 CMA9 + 1 non-CMA9) and incomplete data. Requirement of 6 consecutive months of data for 60-80% of market not fulfilled, potentially putting Nov deadline at risk. ASPSP roundtable organized 1st August and questionnaire sent that same day. 11 responses received by 15/08 deadline (69% of those contacted). Early summary of responses provided to JROC on 19/08. Full report sent to JROC on 30/08. |  | 
2b. Financial crime tools (e.g. TRIs) | A | A | G | A | Reporting Amber Following delays in TPPs sending data to ASPSPs for the Phase 2 pilot, OBL are proposing to extend the pilot phase to end October, to enable banks to generate more robust findings on the efficacy of TRIs, which requires consistent, long-term TRI data. This compresses the time available to write the final report, but end November remains achievable. | Rebasing milestones with JWIG on 9 September to ratify the decision to extend the pilot (recognising that this has no impact on final delivery timelines) Update to JROC on 13 September, setting out progress Weekly progress calls with pilot participants | Continued monitoring of TRI volumes being sent to the banks to ensure sufficient for robust analysis Continued monitoring of bank implementation of live fraud rules. Planning for sessions to consider longer-term evolution of financial crime tools.
3. Consumer Protection (Disputes) | G | G | G | G | Reporting Green. FCA has now confirmed the exam question, which addresses the lack of clarity on scope. | Publish Scope/approach doc to JROC. Establish co-dependencies with WS5 consumer protection cross-cutting issues. ​ | Progress thinking and finalise scope.​ Review scope internally and then share with FCA for input/sign-off.​ Set up/hold roundtables and develop stimulus materials.​
4. Information Flows | G | G | G | G | Deadline for participants to provide feedback was 22/08. Low level responses so one final chaser was sent this week which saw 3 further replies. OBL will continue to chase outstanding CMA9 until answered. Team continue to engage with ASPSPs and TPPs to understand adoption/implementation plans ahead of publishing a report on status by the end of Sep-24. | Deliver a 'gap analysis report' by end of Sep-24 sharing an ecosystem adoption/implementation status. | Chase organisations that have not replied, particularly CMA9.

## Slide 11: Workstream 5 Status Report (as at 30.08.24)
Workstream |  | RAG Status* |  |  |  | Key Progress Updates | Upcoming Deliverables, Meetings and Focus Areas | Next week
 |  | Overall | Time | Quality | Risks | Include RAG rationale and action plan and any new risks or issues | Key Milestones/Deliverables due in next 4 weeks (as per plan) | Focus Areas for Next Period
5.1. Technical |  | G | G | G | G | Reporting Green. VRP WG engaged to opine on whether Sweeping VRP APIs are sufficient for cVRP wave 1; some optional standards will need to be mandatory under MLA. The technical workstream is tracking technical requirements on PISPs and ASPSPs under the MLA – worked through alongside propositional MLA. Taking a follow up paper to the WG on 5 September regarding Fraud Prevention (e.g. TRIs, ultimate beneficiary), which may require technical/functional uplift from participants. MI information and reporting kick off meeting scheduled 3 September. | Track technical requirements as MLA requirements are agreed. Presenting follow up fraud prevention paper to WG 5 September. MI requirements for WG meeting 19 September. Consider any longer-term technical developments needed for later waves. | MLA MI requirements Commence longer-term roadmap for Wave 2+
5.2. Disputes |  | A | G | G | A | Reporting Amber Awaiting written feedback from WG. VRPIG supportive of recommendation. Intention to start pre-planning for delivery phase now in expectation of support for the recommendation at JROC on 13 September There is additional project delivery complexity due to liability concerns which need to be considered. This will be managed as a new workstream within the delivery plan. | Feedback deadline on 3 Sep Finalised paper to JROC Board on 13 September for decision Development of detailed delivery plan Internal agreement to start work partially at risk | Securing decision from JROC Internal detailed planning Refinement and agreement of unhappy paths – need to schedule Disputes Workshop
5.3. Industry Engagement |  | G | G | G | G | Reporting Green. Work progressing with wider community from September Shared examples of use cases collected through discussions with TPPs to help define Wave 1 sectors | Summarise current status of interested parties to VRP IG Plan engagement with stakeholder groups | Summarise current status of interested parties to VRP IG Plan engagement with stakeholder groups
5.4. MLA & Commercial | 5.4a MLA | G | G | G | G | Reporting Green RFP responses from three bidding law firms have been reviewed and evaluated Pitch presentations with the 3 bidders are being organised for Monday, Sept 2 Agreed that Pay.UK will co-fund the legal expenses to be incurred (50/50), but OBL will be the exclusive contracting entity with the chosen law firm. OBL and Pay.UK will agree terms of this co-funding arrangement via an LOA. Conflicts checks to confirmed with chosen law firm before finalising contract terms with them Progress continues with Business Requirements with all BRs having been defined and policies are being worked through at sequential VRP Working Groups | RFP process completed with a preferred law firm selected Contract terms negotiated, agreed and signed with chosen law firm BRs (propositional and operational) finalised and provided to law firm for MLA drafting Instructions to law firm commenced; law firm commences MLA drafting MLA kick-off workshop to be held with chosen law firm VRP WG feedback on high-level operational BRs due on Sept 5 | Continue to refine BRs and DMS for sharing with law firm Hold regular project meetings with law firm to progress MLA 1.0 and guidance notes drafting Provide additional instructions/directions to law firm as needed Review drafts as it becomes available Continue to engage with PSR on economic model work and engagement of expert as required
 | 5.4b Comm Framework | ON HOLD |  |  |  | Reporting as on-hold because of the dependency on JROC's response to the call for views and clarity on the workstream deliverables. | Define the deliverables required following review of the PSR’s consultation output. | To get better understanding of the regulatory vs OBL/Pay.UK proposed approach to getting a starting commercial rate.
Workstream RAG | This Week | Last Week
 | Overall | Overall
5.1. Technical | G | G
5.2 Disputes | A | A
Workstream RAG | This Week | Last Week
 | Overall | Overall
5.3 Industry Engagement | G | G
5.4a MLA | G | G
5.4b Commercial Framework | ON HOLD | 
RAG Definitions: | Overall (Based on Time, Quality and Risk RAGs) | Time/Schedule (on track to meet agreed deadlines) | Quality (confidence that the deliverables will meet JROC expectations) | Risks (risk to delivery)

## Slide 12: Return to Green (RTG) Status Report (as at 30.08.24)
Workstream | RAG Status | Reason for non-Green status | Return to Green plan List out specific actions, dates, and owners (including any non-OBL action owners) |  |  | Overall RTG date
 | Overall | Detailed Description/Reason - should be comprehensive and clear | Itemised action plan | Action owners | Action target completion data | 
WS 1 – Levelling Up | R | Reporting Red, to highlight the lack of confidence in the data available or expected to be received in time to support the workstream deliverables. Non-Order workplan objective is to analyse 6 consecutive months of data representing 60-80% of the market by 1 Nov. Handful of submissions received to date, incomplete data set, quality issues, and far from reaching the market representation threshold. Enough useable overlapping data across submissions is required to produce a meaningful analysis. Keeping in mind this is a voluntary submission exercise. | Flagged Nov. deadline risk to JROC. JROC will decide next steps and potential impact on timeline based on TPP’s responses to WS1 survey. TPP roundtable took place on 01-Aug to mitigate the data risk and to help inform JROC on next steps, incl. potential FCA 'voluntary data request’. Survey sent to 23 TPPs, with a 15/08 deadline. Send ecosystem feedback summary report to JROC w/c 26/08 subject to JROC requirements. JROC’s decision on FCA data request, voluntary vs. mandatory, scope (number of non-CMA9 and TPP returns OBL can expect (resourcing & budget implications)), data period requested (last 6M vs. monthly as of start date), expected date of first submission given to participants. Gather TPPs & ASPSPs intentions to submit data by the start date. Reassess impact on ‘non-order workplan’ timeline: if monthly submissions, will require date when OBL starts getting data for 60-80% of market (note: this might later than the start date) + 6M. Agreement on revised timeline and get budget to resource work (external contractors and/or API build. | OBL OBL OBL OBL JROC JROC OBL JROC or JPIG | 29/07/24 - done 01/08/24 - done 15/08/24 - done 30/08/24 – done TBD TBD TBD TBD | TBD
WS2a - Financial Crime Data | A | Reporting Amber, noting a risk of not receiving substantive data in time to fulfil the workstream deliverables, however, confidence in expected data is higher than for WS1. Non-Order workplan objective is to analyse 6 consecutive months of data representing 60-80% of the market by Nov. Data received to date only covers 52%. OBL expects to be in a position to provide a report by Nov., however not the quality level expected to meet the workplan objective. Keeping in mind this is a voluntary submission exercise. | Flagged Nov. deadline risk to JROC. JROC will decide next steps and potential impact on timeline based on ASPSP’s responses to WS1 survey. ASPSP roundtable took place on 01-Aug to mitigate the data risk and to help inform JROC on next steps, incl. potential FCA 'voluntary data request’. Survey sent to 16 ASPSPs, with a 15/08 deadline. Send ecosystem feedback summary report to JROC w/c 26/08. JROC’s decision on FCA data request, voluntary vs. mandatory, scope (number of ASPSP returns OBL can expect (resourcing & budget implications)), data period requested (last 6M vs. monthly as of start date), expected date of first submission given to participants. Gather ASPSPs intentions to submit data by the start date. Reassess impact on ‘non-order workplan’ timeline & budget. Agreement on revised timeline and budget, if any. | OBL OBL OBL OBL JROC JROC OBL JROC or JPIG | 29/07/24 - done 01/08/24 - done 15/08/24 – done 30/08/24 –done TBD TBD TBD TBD | TBD
5.2 Disputes | A | Reporting amber for two reasons: Time pressure on achieving a decision from JROC. OBL has support from VRPWG and VRPIG, but JROC is the critical decision Potential liability concerns over the development and operation of disputes system | Complete options analysis of dispute tools and produce proposals for JROC decision on tool, operator, etc JROC decisions on the choice of dispute tool solution & operator & arbitration approach, solution, & operator. Replanning activities to align and update the delivery plan with the JROC decisions made on the 13/09. | OBL JROC OBL | 22/08/24 13/09/24 30/09/24 | 30/09/24

## Slide 13: Return to Green (RTG) Status Report (as at 30.08.24) – 2/2
Workstream | RAG Status | Reason for non-Green status | Return to Green plan List out specific actions, dates, and owners (including any non-OBL action owners) |  |  | Overall RTG date
 | Overall | Detailed Description/Reason - should be comprehensive and clear | Itemised action plan | Action owners | Action target completion data | 
2b. Financial crime tools |  | Due to issues with the volume, range and consistency of TRIs sent by TPPs to ASPSPs, banks have highlighted concerns that they will not be able to complete robust efficacy analysis by the end of September OBL are proposing to extend the pilot period by 1 month to give more time to build and refine the efficacy analysis being conducted by the banks. This will ensure OBL has robust analysis on which to base the final recommendations. The time to write the final report can be compressed meaning that this has zero impact on final delivery milestones. | Fix data provision issues with TPP’s Extend pilot period to end October and truncate evaluation period, (no impact on critical milestone) Work closely with TPPs and ASPSPs to ensure that this extended time period is sufficient to enable robust analysis to be undertaken | OBL JWIG OBL | 30/08/24 - Complete 09/09/24 30/10/24 | 13/09/24

## Slide 14: 4. Disputes mechanism recommendation

## Slide 15: Dispute System Evaluation: Scoring Summary
Timing
Can the solution be delivered within 6 months?
Core Functionality
Can solution meet the 9 mandatory requirements?
Cost
What will solution cost to develop and operate?
Evaluation Criteria
Score from other 7 evaluation criteria
Email
Yes
No: system only meets 3 out of 9 of the mandated technical requirements.
Yes: can be delivered by early 2025
9/9
90 / 100
£75,000 to develop and a maximum of £50,000 to run.
96/100
Marginal: could be delivered by Mar 25, but dependent on other delivery completing on time
9/9
60 / 100
Up to £500,000 to develop and a maximum of £50,000 to run.
92/100
No. Timing uncertain, but would be significantly longer than 6 months
No: Sores 7/9
No. Timing uncertain, but would take much longer than 6 months.
9/9
New Workflow using existing platform (Salesforce Service Desk System)
New Workflow using existing platform (RCMS – APP Dispute System)
New Workflow using existing platform (PSW, Direct Debit Dispute System)
Externally procured new / existing / reconfigured commercial solution
Not scored: does not pass mandatory functional evaluation.
Not scored: does not pass mandatory functional evaluation.
Not scored: does not pass timing requirement by a significant margin.
R
G
G
G
G
R
R
R
A
G

## Slide 16: Disputes mechanism recommendation
This analysis therefore excludes three options:
Email: fails to deliver a number of mandatory functional requirements. We considered both a “point to point” email solution and a centralised mailbox operated by the MLA Operator, and both variants fail on multiple criteria, most obviously the issues of security, notifications and monitoring.
PSW (Direct Debit Solution): this fails on one specific functional requirement, in that the Direct Debit solution is mono-direction (ie from the payer’s bank to the sponsoring bank). Additionally, PSW is operated by Vocalink and developing / adapting this solution would take considerably longer than 6 months. For both these reasons, this solution has been excluded.
Commercial Solution: running a process to externally procure a solution would take considerable time, even before considering the final costs of the solution which would be unknown until the process was complete. Using an external platform would introduce additional risk. For these three reasons, this option has been excluded.
Rejected Systems
Both Salesforce and RCMS meet the functional requirements,
Both Salesforce and RCMS could be delivered in 6 months (albeit with some risk in the case of RCMS).
Both Salesforce and RCMS score very similarly on evaluation criteria
We therefore conclude that cost to deliver is the most important factor for consideration, with the adaptation of the RCMS solution forecast to cost up to £500,000 versus £75,000 for the Salesforce solution
We therefore recommend the Salesforce based option
Candidate Solutions and Final Conclusion

## Slide 17: Supporting Rationale
This solution meets the functional requirements as currently understood but represents a relatively small cost to build and operate.
It will not slow down the rollout of cVRP as it can be operational by early 2025.
The volume, type and complexity of disputes under Wave 1 cVRP is not yet fully understood. Committing significant investment with this lack of knowledge would not be prudent in our view.
We are also extremely mindful of the learning from the Open Banking Dispute Resolution Mechanism, built as part of the CMA Order. This system was built in the expectation of a high volume of disputes, but usage was very low and it was decommissioned several years later.
We consider Salesforce to be an appropriate “bridging solution” which can meet the needs of Wave 1 and potentially Wave 2, whilst also providing the data and tracking to be able to more accurately determine when a long-term solution will be required and the precise functionality that will be required.
We recognise that migrating from one solution to another represents some cost and complexity for participants, but we do not consider this to be a valid reason to commit greater cost to a more complex solution from Day 1

## Slide 18: Feedback Summary & Next Steps
We received 7 pieces of feedback on the recommendation paper from 22 August
Overall: 4 endorsed the findings and process; 2 were partially endorsed; and 1 challenged.
The strongest challenges related to the process we have followed:
  Questions relating to how we have managed conflict of interest
  Challenges on the scoring methodology and the focus on time to market
  The failure to run a full RFP process to establish potential commercial solutions that could meet the needs of Wave 1
In terms of the actual recommendation:
  One piece of feedback suggested that the Salesforce “bridging solution” should be for short term use only with a commitment to run a comprehensive RFP process prior to Wave 2.
  Another agreed that a “bridging solution” was needed, but that this could be email.
We had useful feedback on potential impacts on consumers. This will be a major focus in the Disputes Framework / Unhappy Paths workstream
We are now drafting the JROC paper ready for the 13 September meeting. We will note dissenting voices and share a copy of the paper.

## Slide 19: 5. MLA operator decision approach

## Slide 20: MLA operator decision approach
 | Sept | Oct | Nov
VRP WG |  |  | 
VRP IG |  |  | 
JROC Board |  |  | 
  The decision on which entity will operate the wave 1 MLA is a key one and one that needs to be made in a timely fashion given the implications for the 2025 funding round and the need for the chosen entity to ready itself for the rollout of the wave 1 VRPs in H1 2025.
  It is important that we take into account stakeholder views and operate a robust process to assess the optimal operator for the MLA.
  In light of this we will run the following process to work through the recommendation, which allows a final decision to be made to the JROC Board in November.
  The following slides provide a high-level overview of the options for the organisation which will operate the MLA and the criteria we plan to use to evaluate the options.
Evaluation criteria
Outline operator options
Functional capabilities for MLA operator
19/09
Operator evaluation – first cut
Seeking feedback from participants
3/10
Finalise recommendation
Feedback by 1 Nov
17/10
Review evaluation criteria, operator options & functional capabilities
27/09
Review operator recommendation
30/10
Feedback window
5/09
Feedback window
Feedback window
Feedback window
Progress update
7/10
Decide on organisation to operate MLA
7/11

## Slide 21: Proposed options for the wave 1 MLA operator
The options for the wave 1 MLA operator are considered to be the following:
Do VRP WG participants agree that these are the full list of options for the MLA operator?
Are there other options that should be considered?
What are your initial views on the feasibility of each of these options?
Pay.UK
New company specifically created
OBL and Pay.UK as joint operators of the MLA
New SPV joint venture company created between OBL and Pay.UK
OBL

## Slide 22: Proposed evaluation criteria
Do VRP WG participants agree that this a full list of criteria for evaluating the choice of the wave 1 MLA operator? Are there additional criteria that should be used in the assessment?
Detailed paper to follow – feedback requested by 18 September
The options are to be assessed against the following evaluation criteria:
Ease of set up and speed to achieve
Cost to set-up and run
Management of liabilities
Alignment with resource and capabilities of the organisation
Wider strategic implications for each organisation
Suitability of the management and governance of the organisation
Future development for waves 2+
Legal issues relating to the organisation in operating the MLA

## Slide 23: 6. Wave 1 sector definition

## Slide 24: Wave 1 Sector Definitions
We are proposing to JRoC that Wave 1 use cases are:
Core use cases:
Payments to utility companies
Payments to regulated financial firms, and
Payments to central and local government
Additional use cases:
Rail Tickets (subject to final review), Charitable donations

## Slide 25: Updated Principles in selecting use cases
cVRP are from UK payment accounts only to a UK account.
Where the biller is from a utility or financial services firm, it needs to be regulated by the relevant sector regulator.
Other firms can be considered for inclusion if they are regulated by a relevant sector regulator and where there are appropriate consumer protections in place e.g. alternate dispute resolution framework or reimbursement requirements.
The cVRP offering needs to meet the way that billers operate e.g. at whole biller/merchant level. A biller/merchant can consolidate multiple goods or services into a single bill but is not allowed to include ecommerce transactions outside the scope of regulatory protections.
Propositions can include both customer present and customer not present options.
Wherever possible, propositions need to unlock benefits for vulnerable consumers. cVRP use cases should not cause any detriment to vulnerable consumers compared with non-vulnerable consumers.

## Slide 26: Utilities
Final Proposals for Utilities
Electricity and Gas – regulated by Ofgem is included.
Water – Ofwat regulated water providers is included.
Telecoms –any regulated firm providing broadband, fixed phone lines or mobile phone contracts.
Any retail purchases are excluded – specifically with relevance to the telecoms sector, this includes purchases bundled with a contract e.g. sky glass.

## Slide 27: Financial services
FSCS protection remains as the key milestone for commercial sweeping, but additional use cases have been included e.g. pensions under the pensions’ regulator and mortgages.
Final proposals for commercial sweeping:
“Me to Me” payments are extended to common law partners/ spouses or dependent children
FCA authorised and regulated financial firms are in scope
TPR Pension funds are in scope
Mortgage accounts are in scope
Any other payments into FSCS protected accounts and products
FCA regulated E-Money Institution current accounts are also included for payments to spouses or dependent children where not covered by sweeping.

## Slide 28: Central and Local Government
Final proposals for central and local government
All central government departments and agencies are included but retail purchase payments are excluded.
All local councils are included also retail purchases are excluded.
Any outsourced third party operating under contract to either local or central government are excluded.

## Slide 29: Other use cases
Purchasing rail tickets - Currently ‘in scope’ but more work to do before a final decision is taken
Post and parcel services – Now out of scope
ATOL and ABTA travel and holidays – remain out of scope
Charities and charitable donations – Remain in scope
[Stretch use case] Lower risk e-commerce – remain out of scope

## Slide 30: 7. Workstream 1 and 2a update

## Slide 31: Workstream 1 ‘Levelling up Availability and Performance’ Update
JROC is looking at next steps, including a potential voluntary data request by the FCA. To help with their assessment, OBL organised a roundtable with 23 TPPs on 1st August and sent them a questionnaire to gather their feedback. 18 firms (78%) responded.
Key findings
Performance & Availability (P&A) is reported as an issue by 78% of respondents, with unplanned downtime and failure rates / abandoned / cancelled payments generating the most pain points for TPPs. Several respondents also reported differences between P&A figures self-reported by ASPSPs and their own experience. 61% of respondents are also experiencing Conversion rate issues (70% for PISPs).
Although a few respondents indicate they currently do not log some of the requested data (e.g. Phase 2 data), the main issue highlighted is that development work would be needed to access and report the requested data. 83% said development would be required or that the data is not available.
56% listed ‘Not Mandatory’ as a reason for not providing data. To pass business case / prioritisation step for non-mandatory work, TPPs would need to see this exercise drive improvements in the ecosystem – e.g. defining upfront a clear process for investigation and possible enforcement for underperforming ASPSPs, understand what powers the regulators have to improve sub-par performance. Some TPPs made their data submission conditional to this.
If data was going to be requested, 67% indicated they would submit Phase 1 or Phase 1 & 2 data, although one only if mandatory and another only if via API.
83% mentioned resourcing issues (people), low priority, or budgeting constraints. Most responses ranged between 14-52 man-days across 1-5 staff members. Non-personnel cost was mentioned by eleven respondents, 9 of which quoting data storage /cloud / infrastructure cost. Many lacked time to conduct a detailed analysis.
Time to start submitting data ranged between days and 12 months, with 71% of responses falling within 1-3 months.
All but one respondent could only provide data going forward, so historic data is not an option.
83% do not see the current Excel/CSV email submission process as a blocker. OBL could investigate offering other tools (e.g. secure file transfer).
Some TPPs proposed alternatives to a data request and the majority of them monitor P&A and Conversion rate via live transactions.
72% of respondents provided examples of data metrics to be reported back, denoting an interest in monitoring the performance of the ecosystem.

## Slide 32: Workstream 1 ‘Levelling up Availability and Performance’ Update
This feedback reinforces a previous conclusion articulated in the Strategic Working Group report that “In order to have an evidence-based approach to resolve some outstanding issues within the OB ecosystem and discuss future development, various stakeholder groups need to have access to up-to-date, consistent data sets to shed light on key issues such as API reliability and fraud.” The fact that TPPs are still reporting significant unresolved issues is disappointing, but the lack of data makes it very difficult for OBL or the FCA to properly evaluate underlying issues and propose proportionate remedial actions.
On one side, TPPs are clearly calling for the need to improve the performance of open banking APIs but on the other, are not necessarily able or ready to prioritise the resources to generate the data necessary to achieve this. Their feedback indicates that TPPs remain unconvinced that relevant actions will flow as a result of the provision of data, which acts as a disincentive to provide it.
Next steps for JROC to consider
Requesting WS 1 Performance & Availability reporting from non-CMA9 ASPSPs.
Adapting existing mandatory reporting (e.g. REPO20) and prescribe the exact P&A and Conversion rate metrics ASPSPs should report to the regulator.
Considering outlining a defined plan that extends beyond the analysis phase to set out commitments to how the findings will be used to inform a concrete set of policy development activities that incentivise TPPs to invest time and effort in supplying data.
Investigating alternatives to a voluntary data request to TPPs, either before issuing the data request or as a potential interim solution until the long-term regulatory framework is in place which mandates reporting, if it becomes clear that a voluntary data request will not generate the volume and quality of data required.
Implementing a ‘stage-gate’ whereby firms will need to confirm by this date whether, what, when, and how they will provide the requested data. Provided a sufficient number of firms enable to reach the >60% threshold, then the data request can proceed. This is key to ensure no TPP wasted effort, there is confidence upfront that enough good quality and consistent data will be available to perform a meaningful analysis. This will also provide clarity to firms already submitting.
As open banking’s adoption becomes increasingly mainstream and payments expand to e-commerce (cVRP), performance and availability should be at par with well-established offering, for instance prevalent payment methods. This maybe post long-term regulatory framework, but to support this it will be important to consider whether the benchmark should evolve from parity with the ASPSP’s own direct channels to competing products/payment methods.
In the meantime, although the data template has already been significantly pared down during the EAG process last year, OBL is reviewing which fields could be categorized as Core vs. non-Core (e.g. TTFB/TTLB).

## Slide 33: Workstream 2a ‘Financial Crime Data’ Update
JROC is looking at next steps, including a potential voluntary data request by the FCA. To help with their assessment, OBL organised a roundtable with 16 ASPSPs on 1st August and sent them a questionnaire to gather their feedback. 11 firms (69%) responded.
Key findings
All are collecting data enabling them to identify fraud cases from Open banking-initiated payments. Some ASPSPs face challenges in reporting mainly due to the request being not mandatory or considered a lower priority, development work being required, data issues (not available / not completely clear), or resourcing.
55% said they would provide a full response if the data collection template was issued by the FCA. ASPSPs that would not submit include a large CMA9.
Most of the data in the OBL template was not reported as problematic, except for four fields highlighted by more than one ASPSP as trickier, especially when covering granular TPP level data. Some of these fields could be made optional in a first phase.
Clearly defining the requested data fields and time window is key to ensure consistency and that meaningful analyses can be performed.
The estimated time to implement the reporting the first time ranges, for most, from 15 days to 3 months, involving between 2 and 7 staff members.
The current Excel/CSV email submission process is not a blocker in most cases. Some ASPSPs were concerned with security and there are ways it could be enhanced for those submissions.
73% of respondents gave suggestions for data metrics they would like to see reported back to the ecosystem, demonstrating an appetite to see fraud data shared via this workstream so that actions can be taken.

## Slide 34: Workstream 2a ‘Financial Crime Data’ Update
Next steps for JROC to consider
Starting to request data focusing on the large ASPSPs. Getting consistent, good quality data monthly from the large ASPSPs who have submitted some data (although some not useable) would help exceed the 60% threshold. Potentially, a couple more ASPSPs would help approach the 80% mark.
Considering a phased approach to allow us to conduct a first level of analysis of open banking payments fraud, from which to build on if relevant. The more problematic fields could be introduced as part of the core request in a second phase, with the understanding that this would have a direct impact on the granularity of the analysis and the findings that could be reported back to the ecosystem.
Setting the data collection frequency to monthly to allow spotting negative trends early. However, smaller ASPSPs said they would like to see data collected less frequently. An option could be given to these smaller ASPSPs to share data every 3 or 6 months. OBL would produce monthly a report based on data from the large ASPSPs, which could then be supplemented twice a year with data from these smaller actors.
Providing a clear articulation and commitment to providing ancillary benefits to contributing firms to incentivise participation and deliver benefits that help offset the time and costs associated with participation.
Implement a ‘stage-gate’ whereby firms will need to confirm by this date whether, what, when, and how they will provide the requested data. Provided a sufficient number of firms enable to reach the >60% threshold, the data request can proceed. This is key to ensure no ASPSP wasted effort, there is confidence upfront that enough good quality and consistent data will be available to perform a meaningful analysis. This will also provide clarity to firms already submitting.
Reviewing existing mandatory fraud reporting to help avoid duplication of efforts.
Offering participants the possibility to submit data via the ‘FCA Reg Data’ secure upload facility.

## Slide 35: 8. Workstream 2b change request – pilot extension

## Slide 36: Workstream 2b change request – pilot extension

## Slide 37: 9. Procurement approach for MLA legal support - update
Classification: CONFIDENTIAL
37

## Slide 38: Legal support procurement update
On August 7, OBL and Pay.UK jointly issued an RFP to select a law firm to support the development of the MLA for Wave 1
Four firms were invited to participate:
  Addleshaw Goddard
  Allen & Overy
  Hogan Lovells
  and Orrick
We gave the firms 2 weeks to respond; over this period Pay.UK were also considering their position in terms of jointly funding the legal workstream.
On August 21, we received bid responses from all firms except Allen and Overy (who had decided not to take part).
Pay.UK also confirmed they pay half of the legal work; although up to a caped maximum level - £TBD.

## Slide 39: Legal support procurement update
An evaluation panel was formed comprising of 5 members (3 from OBL and 2 from Pay.UK)
  This included members representing procurement, policy & strategy, and legal.
The evaluation criteria was set and agreed by the panel (based on pre-existing frameworks) : quality & delivery (30%), experience (30%), account & relationship management (10%), and value for money (30%)
The panel met initially and scored bids, questions that had arisen were sent back to each bidder.
On Monday, 2 Sept, the firms presented their bids to the evaluation panel via Teams calls, including responses to our questions and Q&As. The evaluation panel then did final reviews and scoring.
Addleshaw Goddard (AG) was the clear winner. Based on their qualifications & experience, their past work on other similar arrangements, and their overall capabilities and credentials. Hogan Lovells (HL) was still highly scored on quality and delivery but had less strong experience.
Evaluation panel is confident that AG would be capable of delivering a high-quality MLA framework agreement that would have the best chance of gaining broad acceptance from across the industry
Next Steps
OBL (with agreement from Pay.UK) appointing AG as the preferred law firm to support the MLA development work w/c 9 September.
Onboard AG via OBL & Pay.UK deep dive sessions; expect AG to attend WG meetings and host specific elements of it.

## Slide 40: 10. AOB
Classification: CONFIDENTIAL
40